## Project Parameters
[Company Name]
Project Parameters
Company Confidential
[Date]
Gray cells will be calculated for you. You do not need to enter anything in them.
Project type | Account manager | Project manager | Business analyst | Process specialist | Finance specialist | Administrative staff | Total
| 10% | 20% | 40% | 10% | 10% | 10% | 100%
Business process re-engineering | 10% | 10% | 10% | 50% | 10% | 10% | 100%
Cost reduction | 10% | 20% | 10% | 20% | 30% | 10% | 100%
Process improvement | 10% | 20% | 10% | 40% | 10% | 10% | 100%
Sarbanes-Oxley | 10% | 20% | 20% | 20% | 20% | 10% | 100%
Strategic planning | 10% | 10% | 50% | 0% | 20% | 10% | 100%
Blended rates | 250 | 225 | 200 | 175 | 150 | 50

## Project Planning
[Company Name]
Project Planning
Company Confidential
Gray cells will be calculated for you. You do not need to enter anything in them.
Task Name | Week1 (23/3 - 29/3) | Week 2 (30/3) | Week 3 (6/4) | Week 4 (13/4) | Week 5 (20/4) | Week 6 (27/4) | Week 7 (4/5) | Week 8 (11/5) | Week 9 (18/5) | Week 10 (25/5) | Week 11 (1/6) | Week 12 (8/6) | Week 13 (15/6) | Week 14 (22/6) | Week 15 (29/6) | Week 16 (6/7) | Week 17 (13 | Week 18 (20 | Week 19 (27 | Week 20 (3 | Week 21 (10 | Week 22
1- Testing Grammar for pseudo code | 2%.
2- Testing the Grammar for simple algorithums on command prompt |  | 5%.
3- Complex algorithums and subroutines (commanc prompt) |  |  | 7%. | 8%.
4- GUI and the two tracing windows |  |  |  |  | 12%.
5- highlighting errors in the pseudo code algorithum | [5 empty] | 15%. | 20%.
6- declaring variables in the second window | [7 empty] | 25%.
7- tracing the program line by line | [8 empty] | 30%. | 35%.
8- enhance the tool | [10 empty] | 37%.
9- User testing | [10 empty] | 40%.
10- Write the thesis. | [11 empty] | till the end of the bachelor
TOTAL HOURS